## Ark1
| WOC 5 Calender & milestones in a glance | [5 empty] | Version 02 | 2006-08-01
2006 | june | june | june | june | june | june | july | aug | sep | oct | nov | dec
[8 empty] | S1 | pc | woc5_1 |  | PR
cc1
2007 | jan | fe | mar | apr | may | june | july | aug | sep | oct | nov | dec
|  |  | pc | woc5_2 | cc2 | PR |  |  | woc5_3 | cc3 |  | pcs
[9 empty] | pc |  |  | PR
2008 | jan | fe | mar | apr | may | june | july | aug | sep | oct | nov | dec
|  | woc5_4 | mar: cc4; june: PR; aug: pc; pc sep: woc5_5; PR dec: pcs
|  | pc | pc sep: cc5; PR dec: PR
2009 | jan | fe | mar | apr | may | june | july | aug | sep | oct | nov | dec
|  | P1 | S paper | S2 | D2 | cc6 | D1 |  |  | WGC
|  |  |  | woc5_6 |  | PR | P3 |  |  | PR
P2
pc
MEETINGS DETAILS
PLENARY MEETINGS (For all WOC members) |  |  | july: STEERING GROUP MEETING (Chair, vice chair, secret, SG leaders)
woc5_1 | Plenary meeting WOC5 Copenhagen 12 & 13 Oct 2006 |  | july: S1; aug: Steering group meeting WOC5 Copenhagen 29 August 2006
woc5_2 | Plenary meeting WOC5 Tokyo 19 & 20 April 2007 |  | july: S2; aug: Steering group meeting. Coordination WGC sessions
woc5_3 | Plenary meeting WOC5 Moscow 27 & 28 Sept. 2007 |  | aug: Further meetings will be organised when relevant
woc5_4 | 2008 Feb/marc | Plenary meetings, dates and places to be defined | aug: As the above S2, those will be organised at the same
woc5_5 | 2008 Aug/sept | (preliminary discussions with France, Austria) | aug: place & date as the plenary meetings
woc5_6 | 2009 April |  | july: S paper; aug: Specific steering group meeting for the paper selection
Exact date & place to be defined
PLENARY MEETINGS (WOC chair / sec) |  |  | july: PHONE CONFERENCES (Chair, secret, with Roberto & Andrew)
cc1 | CC Meeting Lima, Peru 16-17 October 2006 |  | july: pc; aug: Focus & Status report chair and sec.
cc2 | CC Meeting Vevey-Montreux, Switzerland 3-4 May 2007 |  | july: pcs; aug: Focus & Status report sec. Only
cc3 | CC Meeting St. Petersburg, Russia 22-23 October 2007
cc4 | CC Meeting Trinidad & Tobago 26-27 March 2008
cc5 | CC Meeting Gyeongju, Korea 22-23 Sept. 2008
cc6 | CC Meeting London, UK 3-5 June 2009
cc7 | WGC Buenos Aires 5-9 October 2009
DEADLINES DETAILS
DEADLINES CALL FOR PAPERS |  |  | july: DEADLINES
P1 | Abstract submission |  | apr: 1 February 2009; july: D1; aug: Committe final report; cc5 nov: 30 July 2009
P2 | Authors notification |  | apr: 2009-04-15; july: D2; aug: Study groups final report; cc5 nov: 30 May 2009
P3 | Authors full paper submission |  | apr: 15 July 2009; july: PR; aug: Progress report from the committee
(due on 15th of the given month)